## Gantt Chart
MedChem — Smart Pharmacy Management System ¦ Project Gantt Chart ¦ Jan 2026 – Apr 2026
# | Task Name | Phase | Start Date | End Date | Weeks | Status | W00 01 Jan | W01 08 Jan | W02 15 Jan | W03 22 Jan | W04 29 Jan | W05 05 Feb | W06 12 Feb | W07 19 Feb | W08 26 Feb | W09 05 Mar | W10 12 Mar | W11 19 Mar | W12 26 Mar | W13 02 Apr | W14 09 Apr
1 | Requirements Gathering | Planning | 01 Jan 2026 | 07 Jan 2026 | 1w | Critical | ▶
2 | System Design & UML Docs | Planning | 08 Jan 2026 | 21 Jan 2026 | 2w | Critical |  | ▶ | ◀
3 | UI/UX & React App Setup | Infrastructure | 22 Jan 2026 | 04 Feb 2026 | 2w | Critical |  |  |  | ▶ | ◀
4 | Firebase DB & Config | Infrastructure | 22 Jan 2026 | 28 Jan 2026 | 1w | Normal |  |  |  | ▶
5 | Auth & Inventory Module | Core Dev | 05 Feb 2026 | 25 Feb 2026 | 3w | Critical | [5 empty] | ▶ |  | ◀
6 | Sales & POS Module | Core Dev | 26 Feb 2026 | 11 Mar 2026 | 2w | Critical | [8 empty] | ▶ | ◀
7 | Notifications & Expiry | Core Dev | 26 Feb 2026 | 04 Mar 2026 | 1w | Normal | [8 empty] | ▶
8 | Reports & Power BI Sync | Core Dev | 12 Mar 2026 | 25 Mar 2026 | 2w | Critical | [10 empty] | ▶ | ◀
9 | System Testing & QA | Finalization | 26 Mar 2026 | 08 Apr 2026 | 2w | Critical | [12 empty] | ▶ | ◀
10 | Final Documentation | Finalization | 09 Apr 2026 | 15 Apr 2026 | 1w | Critical | [14 empty] | ▶
LEGEND: |  | ■ Planning |  | ■ Infrastructure |  | ■ Core Dev |  | ■ Finalization |  | ■ Critical Path